## excel(14)
/Non Project/PSP Fundamentals & Advanced/Program 7
Size Estimating Template (instructions...)
The PROBE Wizard uses Estimated Proxy Size as the basis for generating final estimates for size and time. However, after you last ran the PROBE Wizard, you modified the estimates on this form, causing the Estimated Proxy Size to change. Your current PROBE estimates are based upon the old value of Estimated Proxy Size. To resolve this problem, you should double-check the values in the form below, then run the PROBE Wizard again.
Project Owner | Mario F. VÃ©lez R.
Size Measure | LOC
BASE PARTS |  |  | Estimated |  |  |  |  | Actual
|  |  | BASE | DELETED | MODIFIED | ADDED |  | BASE | DELETED | MODIFIED | ADDED
PSP Tarea3 Clase Modelo MÃ©todo calcularB0 |  |  | 5 | 0 | 1 | 0 |  | 5 | 0 | 1 | 0
PSP Tarea3 Clase Modelo MÃ©todo calcularB1 |  |  | 21 | 5 | 7 | 3 |  | 21 | 5 | 7 | 3
PSP Tarea3 Clase Modelo MÃ©todo calcularRxy |  |  | 27 | 5 | 5 | 0 |  | 27 | 5 | 5 | 0
PSP Tarea3 Clase Modelo MÃ©todo calcularR2 |  |  | 5 | 0 | 2 | 0 |  | 5 | 0 | 2 | 0
PSP Tarea5 Clase Modelo |  |  | 46 | 4 | 0 | 0 |  | 46 | 4 | 0 | 0
PSP Tarea6 Clase Modelo |  |  | 82 | 4 | 0 | 0 |  | 82 | 4 | 0 | 0
add more rows for base parts... | Total: |  | 186 | 18 | 15 | 3 |  | 186 | 18 | 15 | 3
PARTS ADDITIONS |  |  | Estimated | [5 empty] | Actual
|  |  | TYPE | ITEMS | REL. SIZE | SIZE | NR |  | SIZE | ITEMS | NR
Clase Controlador |  |  | Logic | 1 | Medium | 16 |  |  | 24 | 1
Clase Modelo |  |  | Calculation | 3 | Medium | 33.8 |  |  | 38 | 3
Clase Vista |  |  | I/O | 1 | Small | 12.1 |  |  | 12 | 1
Clase Modelo MÃ©todo Organizador |  |  | Logic | 1 | Medium | 16 |  |  | 14 | 1
add more rows for parts additions... |  |  |  | Total: |  | 77.9 |  |  | 88
REUSED PARTS |  |  | Estimated |  | Actual
|  |  | SIZE |  | SIZE
PSP Tarea4 Clase Modelo MÃ©todo calcularMedia |  |  | 10 |  | 10
PSP Tarea3 Clase Modelo MÃ©todo calcularYk |  |  | 5 |  | 5
add more rows for reused parts... | Total: |  | 15 |  | 15
TOTAL SIZE |  | Actual
SIZE
Actual Size of Finished Product: |  | 222
Instructions: During the planning phase, complete the "Estimated" columns in the form above, then use the PROBE Wizard to fill out the fields below.
|  |  | SIZE |  | TIME
Added Size (A): | A = BA + PA |  | 80.9
Estimated Proxy Size (E): | E = BA + PA + M |  | 95.9
Last Estimated Proxy Size: (The value used on the last run of the PROBE Wizard) |  |  | 95.9
PROBE estimating basis used: (A, B, C, or D) |  |  | A |  | A
Correlation: (r2) |  |  | 0.6 |  | 0.87
Regression Parameters: | B0 (size and time) |  | -19 |  | 19.5
Regression Parameters: | B1 (size and time) |  | 1.46 |  | 4.23
Projected Added and Modified Size (P): | P = B0size + B1size * E |  | 121
Estimated Total Size (T): | T = P + B - D - M + R |  | 289
Estimated Total New Reusable (NR): | (sum of NR items) |  | 0
Estimated Total Development Time: | Time = B0time + B1time * E |  |  |  | 0.29514
Prediction Range: | Range |  | 59.6 |  | 0.055556
Upper Prediction Interval: | UPI = P + Range |  | 181 |  | 0.35069
Lower Prediction Interval: | LPI = P - Range |  | 61.5 |  | 0.23889
Prediction Interval Percent: |  |  | 70% |  | 70%
View PROBE Report
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.