## excel(16)
/Non Project/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 17.1 | 6.88 | 14.5
Planned Time | 0.29514 |  | 1899-12-31 18:48
Actual Tiempo |  | 0.32708 | 1899-12-31 22:30
CPI (Cost-Performance Index) |  |  | 0.92
% Reuse | 5.19% | 6.76% | 10.4%
% New Reusable | 0% | 0% | 2.67%
Test Defects/KLOC or equivalent | 9.69 | 0 | 8.92
Total Defects/KLOC or equivalent | 37.2 | 55.6 | 38.6
Yield % | 69.6% | 100% | 73.1%
Code Review Rate | 735 | 130 | 511
% Appraisal COQ | 4.92% | 9.77% | 5.73%
% Failure COQ | 13.5% | 9.55% | 12.9%
COQ A/F Ratio | 0.36 | 1.02 | 0.45
PQI | 0.01 | 0.07 | 0.01
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 03:31 PM el 3/05/2017